## 📌 Instructions
PROJECT MANAGEMENT — UNIVERSAL TEMPLATE PACK
Four templates · One workbook · Adaptable to any project type · PMI / PMBOK Aligned
SHEET | DESCRIPTION
01 – Project Charter | Formally authorises the project. Define objectives, scope, budget, team, and governance. Requires sign-off before work begins.
02 – Risk Register | Identify, score, and track all project risks. Risk Score auto-calculates (Likelihood × Impact). Conditional formatting highlights severity.
03 – Stakeholder Register | Map all stakeholders by power/interest, define engagement strategy, and track attitudes throughout the project.
04 – Implementation Schedule | Plan and track all phases, activities, and milestones. Dropdown Status and % Complete fields. Change log included.
HOW TO USE THIS PACK
1. Start with the Project Charter sheet — complete it before any other document.
2. Open the Risk Register at project kick-off and update it at every status meeting.
3. Complete the Stakeholder Register during initiation; update when stakeholder attitudes change.
4. Fill in the Implementation Schedule during planning; update % Complete and Status weekly during execution.
5. Yellow-highlighted cells are mandatory input fields throughout all sheets.
6. Dropdown menus are provided for key fields (Status, Priority, Power/Interest, etc.).
7. Risk Score in Sheet 02 is auto-calculated. Risk Level is auto-classified by formula.
8. To add a new project, save a copy of this file and rename it: ProjectName_PM_Pack_v1.xlsx
Version 1.0 · PMI / PMBOK Aligned · June 2026 · Prepared by Godwin Kofi Alorvor

## 01 – Project Charter
PROJECT CHARTER
Universal template — fill in the yellow-highlighted fields. Applicable to any project type.
ℹ INSTRUCTION: Replace all [placeholder] text. Yellow cells are mandatory fields. Delete rows that do not apply.
1. PROJECT IDENTIFICATION
| Project Title: | [Enter project title]
| Project ID / Reference: | [GCL-XXX-YYYY-001] |  | Document Version: | [v1.0]
| Project Sponsor: | [Name & Title] |  | Project Manager: | [Name]
| Start Date: | [DD/MM/YYYY] |  | Target End Date: | [DD/MM/YYYY]
| Department / Division: | [Dept] |  | Organisation: | [Org Name]
| Prepared By: | [Name] |  | Date Prepared: | [DD/MM/YYYY]
2. EXECUTIVE SUMMARY
[Provide a 2–4 sentence non-technical overview: what is being done, why, and what the expected outcome is]
3. BUSINESS CASE & PROBLEM STATEMENT
[Describe the problem, opportunity, or need this project addresses. Include measurable evidence where available.]
Expected benefit: [State the measurable business improvement expected from this project]
4. PROJECT OBJECTIVES — Use SMART format: Specific · Measurable · Achievable · Relevant · Time-bound
| # | Objective |  | Success Metric |  | Owner | Target Date
| 1 | [SMART Objective 1] |  | [How will success be measured?] |  | [Owner] | [Date]
| 2 | [SMART Objective 2] |  | [How will success be measured?] |  | [Owner] | [Date]
| 3 | [SMART Objective 3] |  | [How will success be measured?] |  | [Owner] | [Date]
| 4 | [SMART Objective 4] |  | [How will success be measured?] |  | [Owner] | [Date]
| 5 | [SMART Objective 5] |  | [How will success be measured?] |  | [Owner] | [Date]
5. PROJECT SCOPE
5.1 IN SCOPE
| # | Scope Item (What IS included) |  |  |  |  | Notes
| 1 | [Scope item description]
| 2 | [Scope item description]
| 3 | [Scope item description]
| 4 | [Scope item description]
| 5 | [Scope item description]
| 6 | [Scope item description]
5.2 OUT OF SCOPE
| # | Exclusion |  |  | Reason / Deferred To
| 1 | [Exclusion item] |  |  | [Reason / Future phase]
| 2 | [Exclusion item] |  |  | [Reason / Future phase]
| 3 | [Exclusion item] |  |  | [Reason / Future phase]
6. KEY DELIVERABLES
| Deliverable |  | Description |  | Owner | Due Date | Format / Medium
7. BUDGET SUMMARY
| Cost Category |  |  | Estimated Amount | Approved? | Notes
| Personnel / Labour |  |  | 0
| Technology / Software |  |  | 0
| Equipment / Hardware |  |  | 0
| Training |  |  | 0
| Contingency Reserve (10–15%) |  |  | 0
| TOTAL PROJECT BUDGET |  |  | 0
8. PROJECT CHARTER APPROVALS
| Role | Name |  | Signature |  | Date Approved
Project Sponsor
Project Manager
Key Stakeholder

## 02 – Risk Register
RISK REGISTER
Risk Score = Likelihood × Impact (1–5 scale). Scores ≥ 15 must be escalated to Project Sponsor immediately.
ℹ INSTRUCTION: Add one row per identified risk. Review at every project status meeting. Update Status and Last Reviewed columns weekly.
RISK RATING GUIDE
| Rating | Likelihood |  | Impact |  | Score Range |  | Risk Level | Required Action
| 1 – Very Low | Rare — unlikely to occur |  | Negligible effect on objectives |  | 1–4 |  | LOW | Monitor only — review monthly
| 2 – Low | Unlikely but possible |  | Minor effect, easily managed |  | 5–9 |  | MEDIUM | Active mitigation — assign owner
| 3 – Medium | May occur at some point |  | Moderate impact on time/cost/scope |  | 10–14 |  | HIGH | Immediate action — escalate to PM
| 4 – High | Expected to occur |  | Major impact on project objectives |  | 15–19 |  | CRITICAL | Escalate to Sponsor — contingency plan
| 5 – Very High | Almost certain |  | Threatens project viability |  | 20–25 |  | CRITICAL | Escalate to Sponsor — consider stop/go
RISK REGISTER
| Risk ID | Category | Description | Likelihood (1–5) | Impact (1–5) | Risk Score (Auto) | Risk Level | Mitigation Strategy | Contingency Plan | Risk Owner | Status | Last Reviewed
| R-001 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-002 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-003 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-004 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-005 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-006 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-007 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-008 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-009 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-010 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-011 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-012 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-013 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-014 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN
| R-015 |  | [Describe the risk — what could go wrong and why] | 1 | 1 | 1 | LOW | [Mitigation actions to reduce likelihood or impact] | [What will be done if the risk materialises?] |  | OPEN

## 03 – Stakeholder Register
STAKEHOLDER REGISTER
Identify · Analyse · Engage · Monitor — Update whenever stakeholder roles or attitudes change.
ℹ INSTRUCTION: Complete Identification table first, then Engagement Strategy for all HIGH power or HIGH interest stakeholders.
POWER / INTEREST MATRIX — Use to determine engagement strategy for each stakeholder
| Quadrant | Power | Interest | Strategy |  | Approach
| MANAGE CLOSELY | High | High | Active partner — involve in all key decisions |  | Frequent updates, regular 1-on-1s, involve in reviews
| KEEP SATISFIED | High | Low | Meet core needs — keep informed at high level |  | Periodic high-level updates; avoid overloading
| KEEP INFORMED | Low | High | Regular updates — watch for influence shifts |  | Newsletters, group briefings, feedback channels
| MONITOR | Low | Low | Minimal engagement — check in quarterly |  | Add to distribution lists; review quarterly
STAKEHOLDER IDENTIFICATION REGISTER
| ID | Stakeholder Name / Group | Organisation / Role | Type | Power (H/M/L) | Interest (H/M/L) | Matrix Quadrant | Attitude | Primary Concerns & Expectations | Preferred Channel | Status
SH-01
SH-02
SH-03
SH-04
SH-05
SH-06
SH-07
SH-08
SH-09
SH-10
SH-11
SH-12
STAKEHOLDER ENGAGEMENT STRATEGY — Complete for all HIGH power or HIGH interest stakeholders
| SH ID | Stakeholder Name / Group | Key Message |  | Method | Owner | Next Action | Target Date | Notes

## 04 – Implementation Schedule
IMPLEMENTATION SCHEDULE & MILESTONE TRACKER
Universal project schedule — update % Complete and Status at every weekly status meeting.
ℹ INSTRUCTION: Fill in Phase names, activity descriptions, and dates. % Complete and Status columns must be updated weekly during execution.
SCHEDULE SUMMARY
| Project Title: | [Enter project title]
| Project Manager: | [Name]
| Project Start Date: | [DD/MM/YYYY]
| Target Completion Date: | [DD/MM/YYYY]
| Schedule Version: | 1.0
| Last Updated: | [DD/MM/YYYY]
STATUS DEFINITIONS
| NOT STARTED |  | IN PROGRESS |  | AT RISK |  | DELAYED |  | COMPLETE |  | ON HOLD
KEY MILESTONES
| # | Milestone Description |  | Target Date | Actual Date | Status
| M1 | [Milestone 1 description]
| M2 | [Milestone 2 description]
| M3 | [Milestone 3 description]
| M4 | [Milestone 4 description]
| M5 | [Milestone 5 description]
| M6 | [Milestone 6 description]
| M7 | [Milestone 7 description]
| M8 | [Milestone 8 description]
PHASE 1: [Phase Name — e.g. Discovery & Planning] ¦ Duration: _______ weeks ¦ Phase Owner: _______________________
| Activity ID | Activity / Task Description | Predecessor / Dependency | Assigned To | Planned Start | Planned End | Days | % Complete | Status | Notes / Issues
| P1-001 | [Activity description for task 1] | [5 empty] | 0% | NOT STARTED
| P1-002 | [Activity description for task 2] | [5 empty] | 0% | NOT STARTED
| P1-003 | [Activity description for task 3] | [5 empty] | 0% | NOT STARTED
| P1-004 | [Activity description for task 4] | [5 empty] | 0% | NOT STARTED
| P1-005 | [Activity description for task 5] | [5 empty] | 0% | NOT STARTED
| P1-006 | [Activity description for task 6] | [5 empty] | 0% | NOT STARTED
| P1-007 | [Activity description for task 7] | [5 empty] | 0% | NOT STARTED
| P1-008 | [Activity description for task 8] | [5 empty] | 0% | NOT STARTED
PHASE 2: [Phase Name — e.g. Design & Architecture] ¦ Duration: _______ weeks ¦ Phase Owner: _______________________
| Activity ID | Activity / Task Description | Predecessor / Dependency | Assigned To | Planned Start | Planned End | Days | % Complete | Status | Notes / Issues
| P2-001 | [Activity description for task 1] | [5 empty] | 0% | NOT STARTED
| P2-002 | [Activity description for task 2] | [5 empty] | 0% | NOT STARTED
| P2-003 | [Activity description for task 3] | [5 empty] | 0% | NOT STARTED
| P2-004 | [Activity description for task 4] | [5 empty] | 0% | NOT STARTED
| P2-005 | [Activity description for task 5] | [5 empty] | 0% | NOT STARTED
| P2-006 | [Activity description for task 6] | [5 empty] | 0% | NOT STARTED
| P2-007 | [Activity description for task 7] | [5 empty] | 0% | NOT STARTED
| P2-008 | [Activity description for task 8] | [5 empty] | 0% | NOT STARTED
PHASE 3: [Phase Name — e.g. Development / Execution] ¦ Duration: _______ weeks ¦ Phase Owner: _______________________
| Activity ID | Activity / Task Description | Predecessor / Dependency | Assigned To | Planned Start | Planned End | Days | % Complete | Status | Notes / Issues
| P3-001 | [Activity description for task 1] | [5 empty] | 0% | NOT STARTED
| P3-002 | [Activity description for task 2] | [5 empty] | 0% | NOT STARTED
| P3-003 | [Activity description for task 3] | [5 empty] | 0% | NOT STARTED
| P3-004 | [Activity description for task 4] | [5 empty] | 0% | NOT STARTED
| P3-005 | [Activity description for task 5] | [5 empty] | 0% | NOT STARTED
| P3-006 | [Activity description for task 6] | [5 empty] | 0% | NOT STARTED
| P3-007 | [Activity description for task 7] | [5 empty] | 0% | NOT STARTED
| P3-008 | [Activity description for task 8] | [5 empty] | 0% | NOT STARTED
PHASE 4: [Phase Name — e.g. Testing & Validation] ¦ Duration: _______ weeks ¦ Phase Owner: _______________________
| Activity ID | Activity / Task Description | Predecessor / Dependency | Assigned To | Planned Start | Planned End | Days | % Complete | Status | Notes / Issues
| P4-001 | [Activity description for task 1] | [5 empty] | 0% | NOT STARTED
| P4-002 | [Activity description for task 2] | [5 empty] | 0% | NOT STARTED
| P4-003 | [Activity description for task 3] | [5 empty] | 0% | NOT STARTED
| P4-004 | [Activity description for task 4] | [5 empty] | 0% | NOT STARTED
| P4-005 | [Activity description for task 5] | [5 empty] | 0% | NOT STARTED
| P4-006 | [Activity description for task 6] | [5 empty] | 0% | NOT STARTED
| P4-007 | [Activity description for task 7] | [5 empty] | 0% | NOT STARTED
| P4-008 | [Activity description for task 8] | [5 empty] | 0% | NOT STARTED
PHASE 5: [Phase Name — e.g. Deployment & Closure] ¦ Duration: _______ weeks ¦ Phase Owner: _______________________
| Activity ID | Activity / Task Description | Predecessor / Dependency | Assigned To | Planned Start | Planned End | Days | % Complete | Status | Notes / Issues
| P5-001 | [Activity description for task 1] | [5 empty] | 0% | NOT STARTED
| P5-002 | [Activity description for task 2] | [5 empty] | 0% | NOT STARTED
| P5-003 | [Activity description for task 3] | [5 empty] | 0% | NOT STARTED
| P5-004 | [Activity description for task 4] | [5 empty] | 0% | NOT STARTED
| P5-005 | [Activity description for task 5] | [5 empty] | 0% | NOT STARTED
| P5-006 | [Activity description for task 6] | [5 empty] | 0% | NOT STARTED
SCHEDULE CHANGE LOG — Record all approved changes to the baseline schedule here
| Change # | Date | Activity / Phase Affected |  | Revised Date | Reason for Change | Approved By
CH-001
CH-002
CH-003
CH-004
CH-005
CH-006